## Global
Date | PO | Catégorie | Action | Colonne1 | Customer | Requester | Techmac Resp | Dead line | Status | Note | Installation/F | Réparation | Développement | Livraison
27/09/24 | 202400838 |  | commercial |  | Acs TAc | lahcen | Amine |  | Done | offer send and our costumer oder the part PO 454610415
21/10/2024 |  |  | TDR701 |  | sews mfz | Shinmaywa | Amine |  | Done | 1 week track the machine after updating
28/10/2024 |  |  | TDR701 |  | sews mfz | Shinmaywa | Amine |  | Done | 1 week track the machine after updating
2024-04-11 |  |  | OES CPM5000 |  | Aptiv Kenitra | Mofid | Amine |  | done | installation and testing
2024-11-11 |  |  | Upgrade software machine |  | sews mfz | Shinmaywa | Amine |  | Done | track the machine after updating
19/11/2024 |  |  | Mecmesin |  | kroscho | hachim | Amine |  | Done | change the part damaged
19/11/2024 |  |  | Upgrade software machine |  | sews mfz | Shinmaywa | amine |  | Done | installation the new software for camera
22/11/2024 |  |  | Upgrade software CPM5000 |  | Aptiv dasm | leghnimi | Amine |  | Done | windows activé
25/11/2024 |  |  | Schafer damaged wire issue |  | voltaira | elhaouasse | Amine |  | notyet | wait feedback our partner
21/11/2024 |  |  | Calibration schafer |  | voltaira | elhaouasse | amine |  | Done | Done
14/10/2024 |  |  | upgrade hardware machine |  | sews mfz | Shinmaywa | Amine/rachidi |  | Done | 1 week add new system camera
2024-12-11 |  |  | PAL 4000 |  | Sews cabin | Aziz / Tayan | Amine/rachidi |  | 1. our part is done 2. not yet | 1. problem with Screen (Soussi needs to send quote) 2. battry problem (tayan needs to set a date for diagnoses)
24/09/2024 |  |  | installation et formation |  | voltiatra |  | ben taleb |  | l'installation est fait | il reste la formation
27/09/24 |  |  | formation |  | Gentherm |  | ben taleb |  | ok | deja fait l'insttalation et formation
2024-03-10 |  |  | validation CP de stopre de RBK |  | aptiv M5 |  | ben taleb |  | ok
2024-03-10 |  |  | validation et modification de press at line |  | aptiv M7 |  | ben taleb |  | ok
2024-04-10 |  |  | installation et formation |  | te Tac 1 |  | ben taleb |  | l'installation est fait | deja fait l'insttalation et formation le
2024-07-10 |  |  | daignostque de la machine 10XT |  | Yzaki km9 |  | ben taleb |  |  | deja envoyer l'offre
2024-08-10 |  |  | validation de machine FTM-TP |  | lear tac 2 |  | ben taleb |  | PB de programme
13/11/2024 | K2079869 |  | 3 Jig |  | Lear Kenitra |  | ben taleb |  | Done | deja livrer a techmac zf
13/11/2024 | 4514143238 |  | Reparation 5 mecrometer |  | Yazaki Tanger |  | ben taleb |  | done | sera liver le semaine 49
14/11/2024 | 454603219 |  | 5 Cold metal press |  | Aptiv dasm | Roway | ben taleb |  | Done | sera liver le 27/11/2024 a techmac zf
19/11/2024 | K2098829 |  | Development of Test clip Advanced Force Gauge 500N |  | Lear Kenitra |  | ben taleb
21/11/2024 | 454609716_1000weux |  | Electrified orientation system |  | APTIV ouijda | Mansouri + ismail | ben taleb
2024-08-11 |  |  | Installation of MECMESIN OMNI TEST 25 |  | voltaira | elhaouasse | ben taleb |  | Done
|  |  | develepment de 2 chambre stcs-vmir |  | loeni bouznika | khalid | ben taleb |  | Done
|  |  | devlepement de deux base pour fixatation de tabl X/Y |  | voltaira | alhawas | ben taleb |  | Done
|  |  | devlepement de deux base pour fixatation de tabl X/Y |  | te tac | marouan | ben taleb |  | Done
|  |  | formation de machine omni tornado |  |  |  | ben taleb |  | a confermer | a fixer la date de formation
|  |  | develepment de 2 jig |  | APTIV ouijda | ismail | ben taleb |  |  | deja lancer au fabrication
|  |  | instalation de systeme de foidessement pour STCS-RT |  | Yazaki ZF | dalimi | ben taleb | done |  | sera planifié le 28/11/2024
|  |  | modification d'un jig |  | fujikura kenitra | sofaine | ben taleb |  |  | on a recu la cmd
|  |  | formation de la machine taping-machine |  | leoni berrchid | jamal | ben taleb |  | Done | deja fait
|  |  | develepment de disc de grommet |  | aptiv M7 | amine | ben taleb |  |  | deja envoyer l'offre
|  |  | modification deux de jig |  | fujikura tanger | abdlghafore | ben taleb |  | done | deja fait
|  |  | devlepement de deux pince pour pill and peel |  |  |  | ben taleb |  |  | deja envoyer l'offre
17/09/24 |  |  | Quality validation for TRD701 |  | SEBN | Shinmaywa | Rachidi | Done | 4 Jobs done | Nada sent the report (report in our favor)
|  |  | Diagnoses scheafer 4 machines |  | Leoni |  | Rachidi |  | Done
30/09/24 |  |  | Reparation of Kern balance |  | TE Tac 2 | Bouchaib | Rachidi | - | Standby | Mesbahi will bring a new PCB Board
|  |  | Diagnoses scheafer 6 machines |  | voltaira |  | Rachidi |  | Done
2024-11-11 | 2729857857 |  | Calibration schafer |  | TE Tac 1 | Abdelhaq | Rachidi |  | Done | BL deliverd to Mohammed
2024-11-11 |  |  | Upgrade Machine |  | Sews cabin | Shinmaywa | Rachidi |  | Done
2024-11-11 | M2093411 |  | Waterproof |  | Lear Meknes | Wasima
2024-12-11 | 4514149125 |  | Reparation mecrometer |  | Yazaki Tanger |  | ben taleb
2024-12-11 |  |  | STCS-EHMir Trainning |  | Sews cabin | Natarcia | ben taleb |  | Done
14/11/2024 |  |  | VIMR+ calibration issue |  | Yazaki | Lamrabat
14/11/2024 | 454511273 |  | Expander damag the grommet |  | Aptiv dasm | Roway | ben taleb
19/11/2024 | 4500177955 |  | Installation of MECMESIN OMNI TEST TOUCH 2.5 KN |  | voltaira | elhaouasse | ben taleb |  | done | deja fait
22/11/2024 |  |  | Mecmesin calibration msg |  | Yazaki km9 | Bouchaib | ben taleb |  | deja env
25/11/2024 | K2105707 |  | 16 RT Jigs |  | Lear Kenitra | Salim | ben taleb
25/11/2024 | z/241201443 |  | Gripper DEVLOPMENT 10XT Gripper DEVLOPMENT 5XT |  | MFZ |  | ben taleb
|  |  | calibration de 3 press |  | acs | elharas adil | ben taleb |  | Done
|  |  | calibration de press schefare |  | acs | elharas adil | ben taleb |  | Done
28/11/2024 |  |  | upgrad the machine software and hardware and maintenance both crimper |  | Sews Mfz | shinmaywa | Amine |  | Done | All pint is done :1) Modification of Wire Inlet: for Reduction of Area 2) Maintenance of Crimper 3) Update software for Trimming issue
|  |  | devlepement CP pour arrachement de deux tupe de terminal |  | voltaira | elhaouad+augstun | ben taleb |  | done
25/11/2024 |  |  | problem the touch screen cpm5000 |  | aptiv kentra | moufid | amine |  | Done | • CMP5000 SN: 334I10013/F258 ok• CPM5000 SN: 334H02014/F258 : waiting new screen under warranty
|  |  | formation et insttalation de la machine evo 500 flex |  | leoni ain sabaa | hecham | ben taleb |  | Done | deja fait
|  |  | instalation de systeme ups pour 5 machineS STCS-RT |  | aptiv kentra | berricha | ben taleb |  | Done | deja fait
2024-09-12 | M2118997 |  | STCS-HM400V2Installation & training |  | Lear Meknes | Karim Zinbi |  |  | notyet | waiting feedback the receive machine
2024-09-12 |  |  | Table |  | APTIV oujda |  | Rachidi/Rachid |  | done
|  |  | pb de bloquage de logiciel VectorPro |  | lear tanger | chakir | ben taleb |  |  | deja regler le problem il reste de progrmmer le rapport demander par lear
|  |  | pb de cable de communication de celle de charge de la machine omni tst 1.0 N |  | lear tunsia | Rahma | ben taleb |  |  | voir avec mecmesin l'envoi de cable sous garantier

## Feuil5
Installation
Réparation
Développement